## Current Iteration
|  | Iteration Number: |  |  |  | 1
|  | Expected Total effort: |  |  |  | 77
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Consultar lugares de Atención | 13 | Days (Points Completed) 1: 5; Days (Points Completed) 2: 3; Days (Points Completed) 3: 1; Days (Points Completed) 4: 1; Days (Points Completed) 5: 2; Days (Points Completed) 6: 1 | 0 | 100%
Visualizar disponibilidad en el detalle del lugar de atención | 13 | Days (Points Completed) 7: 3; Days (Points Completed) 8: 5; Days (Points Completed) 9: 3; Days (Points Completed) 10: 2 | 0 | 100%
Ubicación del usuario | 8 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 5; Days (Points Completed) 5: 1 | 0 | 100%
Visualizar disponibilidad en listado de lugares de atención | 8 | Days (Points Completed) 4: 5; Days (Points Completed) 5: 3 | 0 | 100%
Registrar Nuevo Usuario | 5 | Days (Points Completed) 5: 3; Days (Points Completed) 6: 2 | 0 | 100%
Correo de registro | 5 | Days (Points Completed) 5: 2; Days (Points Completed) 6: 3 | 0 | 100%
Crear lugares de Atención | 5 | Days (Points Completed) 6: 2; Days (Points Completed) 7: 3 | 0 | 100%
Editar lugares de Atención | 5 | Days (Points Completed) 7: 3; Days (Points Completed) 8: 2 | 0 | 100%
Consultar lugares de Atención | 5 | Days (Points Completed) 8: 3; Days (Points Completed) 9: 2 | 0 | 100%
Registrar Nueva EPS | 5 | Days (Points Completed) 9: 3; Days (Points Completed) 10: 2 | 0 | 100%
Actualizar datos básicos de EPS | 5 | Days (Points Completed) 10: 3 | 2 | 60%
Feature 12 | [21 empty] | 0
Feature 13 | [21 empty] | 0
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 77 | 72 | 69 | 66 | 55 | 44 | 36 | 27 | 17 | 9 | 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2 | 97.4%
Ideal Trend | 77 | 69.3 | 61.6 | 53.9 | 46.2 | 38.5 | 30.8 | 23.1 | 15.4 | 7.7 | - | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days