## Current Iteration
|  | Iteration Number: |  |  |  | 2
|  | Expected Total effort: |  |  |  | 39
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
Crear Especialidades Médicas | 5 | Days (Points Completed) 1: 3; Days (Points Completed) 2: 2 | 0 | 100%
Editar Especialidades Médicas | 5 | Days (Points Completed) 3: 2; Days (Points Completed) 4: 3 | 0 | 100%
Actualizar datos básicos de usuario | 3 | Days (Points Completed) 2: 1; Days (Points Completed) 4: 2 | 0 | 100%
Consultar Usuario | 3 | Days (Points Completed) 4: 1; Days (Points Completed) 5: 2 | 0 | 100%
Eliminar lugares de Atención | 3 | Days (Points Completed) 5: 1; Days (Points Completed) 6: 2 | 0 | 100%
Consultar EPS | 3 | Days (Points Completed) 5: 3 | 0 | 100%
Eliminar EPS | 3 | Days (Points Completed) 6: 3 | 0 | 100%
Consultar Especialidades Médicas | 3 | Days (Points Completed) 7: 2; Days (Points Completed) 8: 1 | 0 | 100%
Consultar Especialidades Médicas | 3 | Days (Points Completed) 9: 3 | 0 | 100%
Eliminar Usuario | 2 | Days (Points Completed) 8: 2 | 0 | 100%
Login | 2 | Days (Points Completed) 8: 2 | 0 | 100%
Logout | 2 | Days (Points Completed) 9: 2 | 0 | 100%
Eliminar Especialidades Médicas | 2 | Days (Points Completed) 10: 2 | 0 | 100%
Feature 14 | [21 empty] | 0
Feature 15 | [21 empty] | 0
Feature 16 | [21 empty] | 0
Feature 17 | [21 empty] | 0
Feature 18 | [21 empty] | 0
Feature 19 | [21 empty] | 0
Feature 20 | [21 empty] | 0
Feature 21 | [21 empty] | 0
Feature 22 | [21 empty] | 0
Feature 23 | [21 empty] | 0
Feature 24 | [21 empty] | 0
Feature 25 | [21 empty] | 0
Feature 26 | [21 empty] | 0
Feature 27 | [21 empty] | 0
Feature 28 | [21 empty] | 0
Feature 29 | [21 empty] | 0
Feature 30 | [21 empty] | 0
Effort Remaining | 39 | 36 | 33 | 31 | 25 | 19 | 14 | 12 | 7 | 2 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 100%
Ideal Trend | 39 | 35.1 | 31.2 | 27.3 | 23.4 | 19.5 | 15.6 | 11.7 | 7.8 | 3.9 | 6.2172e-15 | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days